CENTRAL ANALYTICS  —  CASE STUDY

Automated detection of uninsured vehicles — a real-world precedent

Sensys Gatso &

the Oklahoma UVED Program

What they did, the data they used, the notices they sent, how accurate it was —

why it stalled, and how to implement it for Bajaj motor insurance

The first-in-the-world automated uninsured-vehicle enforcement program — and its most useful lesson

Verified as of August 2026 — sources in the Appendix

Internal Review  |  August 2026

Contents

# At a Glance

Between 2018 and 2020, the US state of Oklahoma ran the first automated uninsured-vehicle enforcement program in the world. A private company, Sensys Gatso, provided the cameras and software; the state provided the insurance data. Number-plate cameras read every passing vehicle, checked it against the state’s insurance database, and mailed a notice to owners who appeared uninsured, offering them a way to get insured instead of going to court.

The detection worked — it correctly identified about 22,000 uninsured vehicle owners. But the program stalled in 2020, and the reason is the single most important takeaway for us: it did not fail on camera accuracy. It failed because ignoring the notice carried no real consequence, so too few people paid. As this document shows, India’s court mandate fixes exactly that weakness — which is why Bajaj can succeed where Oklahoma stumbled.

# 1. What Sensys Gatso Did

Sensys Gatso is a large, global traffic-enforcement technology company (best known for speed and red-light cameras). Oklahoma had one of the worst uninsured-driving rates in the US, so in 2016 its legislature created the Uninsured Vehicle Enforcement Diversion (UVED) Program and hired Sensys Gatso to run it as a fully managed service.

The company deployed fixed and mobile Automatic Number Plate Recognition (ANPR/ALPR) cameras across the state. Each camera read number plates, the system checked them against the state insurance database, and owners who appeared uninsured were sent a “Notice to Respond.” The commercial model was performance-based: Sensys Gatso earned $80 out of every $174 notice paid — it was paid only when people complied, not per camera.

| When | What happened |
| --- | --- |
| 2016 | Oklahoma legislature creates the UVED Program |
| Late 2017 | Sensys Gatso wins the contract (~$2M/year, performance-based) |
| 2017–2018 | State must first rebuild its insurance database before launch (caused delay) |
| Nov–Dec 2018 | Enforcement begins — first-in-the-nation automated uninsured-vehicle program |
| 2018–2020 | ~22,000 uninsured owners identified |
| Aug 2020 | Sensys Gatso and the state part ways — low payment compliance made it uneconomic |
| ~2024 | Program relaunched, again with Sensys Gatso and stronger human review |

# 2. What Data They Used

The program joined two very different kinds of data — one from cameras, one from insurers. The quality of the second one decided everything.

| Data | Type | Source | Note |
| --- | --- | --- | --- |
| Number-plate images | Static (captured live) | ALPR cameras (fixed + mobile) | Read every passing plate; only the plate string is needed to start |
| Insured-vehicle list | Dynamic (constantly changing) | Oklahoma Insurance Department database (OID) / OKIVS verification system | The make-or-break input — tells the system who is insured |
| Vehicle owner record | Static | State vehicle registration | To find the registered owner’s address for the notice |

A crucial detail: the data had to be fixed first The program could not even start until Oklahoma spent time rebuilding its insurance database. The state also could not enforce against fleet vehicles, tribal plates, or out-of-state vehicles, because it did not hold reliable insurance data for them. Lesson: you can only enforce where the insurance data is clean and complete.

# 3. How They Used the Data

Two pieces of Sensys Gatso software did the work, and a human-review step sat on top:

- Puls — the detection platform. It merged the live plate reads with the insurance database in real time, checking each plate against the constantly-updating insured-vehicle list to flag likely uninsured vehicles.

- Xilium — the back-office and fulfilment software. It processed the flagged cases and produced and mailed the “Notices to Respond,” and tracked responses and payments.

The pipeline, end to end:

- Capture — a camera reads a number plate.

- Match — Puls checks the plate against the state insurance database.

- Flag & retain — if the plate is not on the insured list, the image is kept and forwarded to the state UVED office.

- Human review — the image is reviewed for accuracy, and (in the relaunched program) two law-enforcement officers check the flagged plate and decide whether to offer diversion.

- Notify — Xilium issues the Notice to Respond to the registered owner.

Two design choices matter here. First, images were kept only as long as needed as evidence, then deleted — a deliberate privacy limit. Second, a human checked every case before a notice went out — a safeguard added because the automated match alone was not reliable enough (Section 5).

# 4. The Notices They Sent

The notice was the heart of the program — and, importantly, it was designed to route people to compliance, not just punish them.

| Feature | Detail |
| --- | --- |
| Name | “Notice to Respond” — mailed to the registered owner |
| Fee | $174 to enter the diversion program |
| The deal (diversion) | Pay the fee, get insured, and keep insurance for two years — and stay out of court |
| The alternative | A court citation for driving uninsured (~$250 plus court costs, and a record) |
| Vendor share | Sensys Gatso received $80 of each $174 paid |
| Tone | A chance to fix the problem, not an automatic fine — deliberately a “lighter touch” |

This “get-insured” pathway is the part most relevant to an insurer: the notice did not just penalise people, it pushed them to buy cover. That is the exact moment where detection turns into a new policy — the commercial opportunity Bajaj would build around.

# 5. Accuracy — What It Was, and Why

There is no single published “accuracy percentage” for the program, but the record is clear about how accuracy behaved and what drove it.

## 5.1 Early on, accuracy was poor — and it hurt

When the cameras first switched on, hundreds of notices were sent to drivers who were actually insured. Wrongly telling insured people they are uninsured is the worst possible error — it creates anger, complaints, and distrust. This is the classic false-positive problem.

## 5.2 Why the errors happened

- Stale insurance data. If the database did not yet show a recent policy, an insured car looked uninsured. (Oklahoma had to rebuild its database before launch for this reason.)

- Plate-read errors. Early cameras misread plates — a single wrong character matches the wrong vehicle, or no vehicle.

- No human check at first. The early process trusted the automated match too much.

## 5.3 How they fixed it

- Better cameras — the hardware was upgraded to read plates more reliably.

- Quality checks on every flagged image before a notice.

- Mandatory human review — officers verify the plate read and the insurance status before any notice is issued.

The accuracy lesson in one line Detection accuracy was not really a camera problem — it was a data-freshness problem plus a missing human check. Once the database was clean and a person reviewed every case, accuracy became good enough to run the program. Cameras are easy; current, correct insurance data plus human review is what makes the answer right.

# 6. Why the Program Stalled — the Real Lesson

Here is the twist, and the most valuable insight in this whole study. The detection worked — about 22,000 uninsured owners were correctly identified. Yet in August 2020 Sensys Gatso and the state parted ways, calling the program not economically feasible.

The reason was not accuracy. It was that ignoring the notice carried no real consequence. In Oklahoma, if a driver simply did not respond, the next step — prosecution by the state — was never properly implemented. So people learned they could ignore the letter. Payment compliance collapsed: in the first half of 2020, only about 36% of flagged owners enrolled, far below the ~90% the business case assumed. With a performance-based contract (paid only when people pay), the economics broke.

THE key takeaway for Bajaj Automated detection is the easy part. It works. The hard part is consequence and payment. A notice with no teeth gets ignored. Oklahoma proved the technology and then proved that technology alone is not enough — you need a real, enforced consequence behind the notice for people to act. (Notably, the program was revived around 2024 with stronger review and process, showing the model works once the gaps are closed.)

# 7. What We Can Derive

| What to copy (it worked) | What to fix (it failed) |
| --- | --- |
| Camera + insurance-database matching reliably finds uninsured vehicles | A notice with no real consequence gets ignored — build in enforced teeth |
| A “get-insured” diversion pathway (route people to cover, not just punish) | Never launch on stale insurance data — fix the database first |
| Human review before every notice (kills false positives) | Don’t trust the automated match alone — it caused wrong notices |
| Clear privacy limits (delete images after use) | Don’t assume high payment rates — model them conservatively |
| A managed-service / performance model can work | Performance pay is dangerous if you don’t control the enforcement step |

In short: Oklahoma de-risked the technology for us. It showed the detection works, showed exactly how accuracy goes wrong (stale data + no human check) and how to fix it, and showed the one thing that must be in place for the whole thing to pay for itself — a real consequence behind the notice.

# 8. How to Implement It for Bajaj Motor Insurance

The Oklahoma story maps almost one-to-one onto India — and India has the one ingredient Oklahoma lacked.

## 8.1 India’s advantage: the teeth are already there

The single reason Oklahoma stalled — no consequence for ignoring the notice — does not apply in India. The Supreme Court’s August 2026 judgment (2026 INSC 793) mandates ANPR linked to the IIB and VAHAN databases, legally-backed e-challans, and enforcement hooks such as blocking fitness/insurance renewal and a “no insurance, no fuel” pilot. That is exactly the enforced consequence Oklahoma was missing. India starts with the hard part solved.

## 8.2 The build — step by step

- Fix the data first (like Oklahoma had to). India’s insurance database (IIB) can lag real policy status by up to ~2 months. Before scaling, build a real-time insurance-status check (query insurers live, in the style of US verification systems) so recently-insured drivers are never wrongly flagged.

- Build the matching engine. The equivalent of Puls: read the plate (ANPR), match against IIB/VAHAN in real time, flag likely-uninsured vehicles.

- Put a human check before every notice. The exact safeguard Oklahoma learned the hard way — confidence threshold on the plate read, a data-latency buffer, and human review before anything is sent. No insured driver should ever get an “uninsured” notice.

- Send a two-layer notice. The government issues the official compliance e-challan (Layer 1). Beside it sits a clearly-labelled Bajaj “get insured in minutes” offer (Layer 2). Never disguise the offer as a government message.

- Convert — this is Bajaj’s prize. Be the “get-insured” pathway Oklahoma routed people to: plate pre-filled, a two-minute purchase, instant e-policy to DigiLocker, and automatic update of the compliance status. This is where a detected uninsured driver becomes a Bajaj customer.

- Define scope honestly. Like Oklahoma, only enforce where insurance data is clean; phase in vehicle types and start with a single pilot state.

## 8.3 Where Bajaj fits

Bajaj’s role is the technology, data and conversion partner to the court-mandated programme — building the real-time insurance-status check and the accurate detection pipeline, and running the compliant “get insured” journey that turns enforcement into policies. Bajaj already has the parts (a parametric/digital claims stack and existing motor scale) to move quickly.

One-line recommendation Copy Oklahoma’s detection-and-divert model, fix the two things that broke it — stale data and no consequence — and note that India’s Supreme Court mandate already fixes the second. Bajaj’s win is to own the real-time insurance-data check and the “get insured now” pathway that converts detected drivers into customers.

# Appendix — Sources

Verified as of August 2026.

- Sensys Gatso authorised to start the UVED program (Puls, Xilium, cameras) — https://www.traffictechnologytoday.com/news/traffic-management/oklahoma-authorizes-sensys-gatso-to-start-its-uninsured-vehicle-enforcement-program.html

- Sensys Gatso press release — program launch and technology — https://www.sensysgatso.com/uploads/files/pr2018/20181026-Press-Release-UVED_eng.pdf

- Sensys Gatso ends UVED contract — ~22,000 identified; “not economically feasible” — https://www.sensysgatso.com/pressreleases/2020/sensys-gatso-usa-meddelar-att-kontraktet-f%C3%B6r-%C3%B6vervakning-av-of%C3%B6rs%C3%A4krade-fordon-uved-i-oklahoma-fullf%C3%B6ljts-och-avslutas

- Early false positives; human review; how the notice works — https://www.readfrontier.org/stories/first-prosecutions-of-uninsured-drivers-caught-on-camera-could-happen-this-year/

- 2024 relaunch — data flow, exclusions, two officers review flagged plates — https://tulsaworld.com/news/local/crime-and-courts/tickets-in-the-mail-thousands-of-uninsured-vehicles-flagged-as-automated-program-launches-to-find/article_92f1f6fc-ea7b-5acb-93cc-8792c301a15c.html

- Enrollment ~36% vs assumptions; ~200,000 uninsured (analysis) — https://marinerresearchgroup.com/tag/rekr/

- About the UVED Program (Oklahoma.gov) — https://oklahoma.gov/dac/about/staff/about-the-uved-program.html

Note: some figures come from the vendor’s own statements (e.g. “results have been strong”, ~22,000 identified) and from third-party analysis (enrollment rates, uninsured counts). Oklahoma’s early uninsured estimate (~26%) was later judged too high (nearer ~10%), a reminder to validate India’s headline 56% with real data before sizing.